## Overview
BG Name | (All) | [9 empty] | BG Name | (All) | [9 empty] | Row Labels | Count of SO Item
[22 empty] | Z4 Frozen - Past | 17
Count of SO Item | Column Labels | [9 empty] | Count of SO Item | Aging | [9 empty] | Z4 Frozen <30days | 25
Row Labels | AU90 | ID90 | KR90 | MY91 | PH90 | SG90 | TH90 | VN90 | NZ90 | Grand Total | Row Labels | PH90 | SG90 | TH90 | AU90 | MY91 | NZ90 | KR90 | VN90 | ID90 | Grand Total | Z4 Frozen <15days | 46
Pending PM confirmation | 5 |  | 4 | 6 | 8 | 8 | 9 |  | 6 | 46 | Z4 Frozen - Past | 1 | 4 | 6 | 2 | 2 |  | 1 | 1 |  | 17 | Grand Total | 88
> 15 days | 5 | 1 | 3 | 2 | 8 | 1 | 3 |  | 1 | 24 | -104 |  | 1 | [7 empty] | 1
RDD move out | 3 | 1 |  | 1 | 1 |  |  | 5 |  | 11 | -47 | [6 empty] | 1 |  |  | 1
#N/A | [5 empty] | 4 | 1 |  |  | 5 | -26 | 1 | [8 empty] | 1
CCD SWAP |  |  |  |  | 1 |  |  |  |  | 1 | -18 |  |  | 1 | [6 empty] | 1
Material Hold in factory | [5 empty] | 1 |  |  |  | 1 | -13 |  |  | 1 | [6 empty] | 1
Grand Total | 13 | 2 | 7 | 9 | 18 | 14 | 13 | 5 | 7 | 88 | -12 | [7 empty] | 1 |  | 1
[11 empty] | -8 |  |  | 1 |  | 1 |  |  |  |  | 2
[11 empty] | -7 |  |  | 2 | [6 empty] | 2
[11 empty] | -4 |  | 2 | [7 empty] | 2
[11 empty] | -3 |  |  | 1 |  | 1 |  |  |  |  | 2
[11 empty] | -2 |  | 1 |  | 2 | [5 empty] | 3
[11 empty] | Z4 Frozen <15days | 9 | 9 | 4 | 5 | 5 | 6 | 3 | 4 | 1 | 46
[11 empty] | 0 |  | 1 | [7 empty] | 1
[11 empty] | 1 |  |  |  | 3 | [5 empty] | 3
[11 empty] | 2 |  | 5 |  | 1 |  | 5 |  |  |  | 11
[11 empty] | 3 | 1 |  | 1 | [6 empty] | 2
[11 empty] | 5 |  |  |  | 1 | 2 |  | 1 |  |  | 4
[11 empty] | 6 |  | 1 |  |  | 1 |  |  |  |  | 2
Z4 Status | (All) | [9 empty] | 7 | 1 |  |  |  | 1 |  |  |  |  | 2
BG Name | IGT-S | [9 empty] | 8 | 2 |  | 2 |  |  |  | 1 |  |  | 5
[11 empty] | 9 |  |  | 1 |  |  | 1 |  |  |  | 2
Count of SO Item | Column Labels | [9 empty] | 10 |  | 1 | [7 empty] | 1
Row Labels | AU90 | ID90 | KR90 | MY91 | PH90 | SG90 | TH90 | VN90 | Grand Total |  | 11 |  |  |  |  | 1 |  | 1 | 1 |  | 3
Charan GS |  |  |  |  | 6 |  | 8 |  | 14 |  | 12 | [8 empty] | 1 | 1
V Thirumalesh | 6 | [7 empty] | 6 |  | 13 | 2 | [6 empty] | 1 |  | 3
Swamynathan s |  |  |  | 5 |  |  |  |  | 5 |  | 14 | 2 | 1 | [5 empty] | 2 |  | 5
Meliza VIda | 4 | [7 empty] | 4 |  | 15 | 1 | [8 empty] | 1
Arun Kumar |  | 1 | [5 empty] | 2 | 3 |  | Z4 Frozen <30days | 8 | 1 | 3 | 6 | 2 | 1 | 3 |  | 1 | 25
MOON HOSUAH |  |  | 2 | [5 empty] | 2 |  | 16 |  |  |  |  | 2 |  | 1 |  |  | 3
Ram Vinna R | [5 empty] | 1 |  |  | 1 |  | 17 |  |  | 1 | 2 |  |  |  |  | 1 | 4
Grand Total | 10 | 1 | 2 | 5 | 6 | 1 | 8 | 2 | 35 |  | 18 | 5 | [8 empty] | 5
[11 empty] | 19 |  |  |  | 1 |  | 1 |  |  |  | 2
[11 empty] | 20 | 2 |  | 1 | [6 empty] | 3
[11 empty] | 21 | 1 |  |  | 1 | [5 empty] | 2
[11 empty] | 22 |  | 1 | 1 | 2 |  |  | 2 |  |  | 6
[11 empty] | Grand Total | 18 | 14 | 13 | 13 | 9 | 7 | 7 | 5 | 2 | 88
Count of SO Item | Column Labels
Row Labels | AU90 | ID90 | KR90 | MY91 | PH90 | SG90 | TH90 | VN90 | NZ90 | Grand Total
Pending PM confirmation | 5 |  | 4 | 6 | 8 | 8 | 9 |  | 6 | 46
> 15 days | 5 | 1 | 3 | 2 | 8 | 1 | 3 |  | 1 | 24
RDD move out | 3 | 1 |  | 1 | 1 |  |  | 5 |  | 11
#N/A | [5 empty] | 4 | 1 |  |  | 5
CCD SWAP |  |  |  |  | 1 |  |  |  |  | 1
Material Hold in factory | [5 empty] | 1 |  |  |  | 1
Grand Total | 13 | 2 | 7 | 9 | 18 | 14 | 13 | 5 | 7 | 88

## Summary
Sales Org | Sales Document | SO Item | Material | Material Description | RDD | PMRDD | SID | CAD | Start Frozen Period Date | Days until Start FP | PO Number | Ship to Customer Name | Owner | Comments - High | Detialed Comments | Project Manager
AU90 | 6600669039 | 10010 | 722226 | Azurion 7 B20 | 2024-09-15 | 2024-09-15 | 2024-09-16 | 2024-10-25 | 2024-04-23 | -2 | 4520140639 | Royal North Shore Hospital | FOM | RDD move out | RDD move out- revised FPD required | Fernandez Jaz
AU90 | 6600617503 | 10010 | 722226 | Azurion 7 B20 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2024-12-13 | 2024-04-23 | -2 | 4518796283 | Royal North Shore Hospital | FOM | RDD move out | RDD move out- revised FPD required | Fernandez Jaz
AU90 | 6600617503 | 10110 | 722367 | DoseAware | 2024-11-01 | (blank) | 2024-11-01 | 2024-12-13 | 2024-04-28 | 2 | 4518796283 | Royal North Shore Hospital | PM | Pending PM confirmation | Email follow up sent to PM | Fernandez Jaz
AU90 | 6600637628 | 20010 | 881101 | Advanced Visualization Workspace(881120) | 2024-06-13 | (blank) | (blank) | 2024-06-30 | 2024-05-01 | 5 | 4520206916 | PERTH RADIOLOGICAL CLINIC-SUBIACO | PM | Pending PM confirmation | Email follow up sent to PM | Sabrina Censi
AU90 | 6600662625 | 10010 | 712035 | DigitalDiagnost C90 Flex/Value/Chest/ER | 2024-07-29 | 2024-07-30 | 2024-08-12 | 2024-09-06 | 2024-05-17 | 17 | 4519960023 | IA Corporation Pty Ltd | - | > 15 days | > 15 days | Peter Bestawrose
AU90 | 6600662625 | 80010 | 728144 | Incisive CT | 2024-07-29 | 2024-07-30 | 2024-08-12 | 2024-09-06 | 2024-05-17 | 17 | 4519960020 | IA Corporation Pty Ltd | - | > 15 days | > 15 days | Peter Bestawrose
AU90 | 6600673265 | 20100 | 718133 | Zenition 70 | 2024-07-05 | 2024-07-05 | 2024-07-15 | 2024-07-19 | 2024-05-21 | 19 | 4520242547 | RADIOLOGYSA SERVICE TRUST | - | > 15 days | > 15 days | Ting David
AU90 | 6600681302 | 10010 | 722467 | Philips Hemo system with IntelliVue X3 | 2024-05-28 | 2024-05-28 | 2024-06-03 | 2024-06-28 | 2024-04-25 | 1 | 4520378519 | ALFRED HEALTH | PM | Pending PM confirmation | Email follow up sent to PM | Consumables PCCI EShop Order
AU90 | 6600681302 | 20010 | 722467 | Philips Hemo system with IntelliVue X3 | 2024-05-28 | 2024-05-28 | 2024-06-03 | 2024-06-28 | 2024-04-25 | 1 | 4520378520 | ALFRED HEALTH | PM | Pending PM confirmation | Email follow up sent to PM | Consumables PCCI EShop Order
AU90 | 6600681302 | 30010 | 722467 | Philips Hemo system with IntelliVue X3 | 2024-05-28 | 2024-05-28 | 2024-06-03 | 2024-06-28 | 2024-04-25 | 1 | 4520378521 | ALFRED HEALTH | PM | Pending PM confirmation | Email follow up sent to PM | Consumables PCCI EShop Order
AU90 | 6600642984 | 10010 | 718133 | Zenition 70 | 2024-07-02 | 2024-07-05 | 2024-07-15 | 2024-07-30 | 2024-05-23 | 21 | 4519469397 | Wyvern Health Pty Ltd | - | > 15 days | > 15 days | Christine Suriyarachchi
AU90 | 6600642984 | 20010 | 718133 | Zenition 70 | 2024-07-02 | 2024-07-05 | 2024-07-15 | 2024-07-30 | 2024-05-24 | 22 | 4519469398 | Wyvern Health Pty Ltd | - | > 15 days | > 15 days | Christine Suriyarachchi
AU90 | 6600654259 | 10010 | 722226 | Azurion 7 B20 | 2024-10-06 | 2024-10-06 | 2024-10-07 | 2024-11-28 | 2024-05-24 | 22 | 4519734315 | GOLD COAST UNIVERSITY HOSPITAL | FOM | RDD move out | RDD move out- revised FPD required | Croft Tom
ID90 | 6600676407 | 10010 | 728144 | Incisive CT | 2024-08-20 | 2024-08-20 | (blank) | 2024-09-20 | 2024-05-10 | 12 | 4520292932 | RSAU Lanud Sulaiman | PM | RDD move out | PM to confirm on the dates. | Mr Rivaldo Sutanto Felix
ID90 | 6600674385 | 10010 | 718096 | Zenition 50 | 2024-07-01 | 2024-07-01 | 2024-07-02 | 2024-08-09 | 2024-05-17 | 17 | 4520280924 | RSUD Taman Husada | - | > 15 days | > 15 days | Mr Rivaldo Sutanto Felix
KR90 | 6600642439 | 10010 | 718075 | BV Endura R2.3 | 2025-03-30 | 2024-03-30 | 2025-03-30 | 2025-04-30 | 2024-02-20 | -47 | (blank) | KOREA UNIV.HOSP.ANSAN | PM | Pending PM confirmation | Order to be debooked by end of April | LIM CS
KR90 | 6600679018 | 10010 | 782111 | Upgrades dStream to R5.7 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2024-06-30 | 2024-05-01 | 5 | 4520328217 | Samsung Medical Center | PM | Pending PM confirmation | Pending Z4OK approval from PM | LIM CS
KR90 | 6600633483 | 10010 | 728144 | Incisive CT | 2024-06-28 | 2023-11-30 | 2024-08-01 | 2024-08-30 | 2024-05-06 | 8 | 4519205405 | M&H | PM | Pending PM confirmation | Pending Z4OK approval from PM | LEE YH
KR90 | 6600633483 | 30010 | 881030 | IntelliSpace IX/LX Workstations | 2024-06-28 | (blank) | 2024-08-01 | 2024-08-30 | 2024-05-24 | 22 | 4519989707 | M&H | - | > 15 days | > 15 days | LEE YH
KR90 | 6600641987 | 10010 | 728144 | Incisive CT | 2024-07-30 | 2024-07-30 | 2024-08-19 | 2024-09-27 | 2024-05-09 | 11 | 4519433563 | Sokcho Medical Center | PM | Pending PM confirmation | Pending Z4OK approval from PM | LEE YH
KR90 | 6600673703 | 20010 | 722137 | Field Extensions Azurion 5 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 2024-08-30 | 2024-05-16 | 16 | 4520236074 | Chonnam National University | - | > 15 days | > 15 days | LEE YH
KR90 | 6600679044 | 20010 | 881011 | Upgrades IntelliSpace Portal | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-08-30 | 2024-05-24 | 22 | 4520331045 | HANYANG UNIV.GURI HOSP. | - | > 15 days | > 15 days | LIM CS
MY91 | 0077482341 | 10010 | 722223 | Azurion 7 M12 | 2024-09-16 | 2024-09-16 | 2024-09-30 | 2024-10-21 | 2024-04-21 | -3 | 4518451574 | KPJ Sabah Specialist Hospital | FOM | RDD move out | RDD revised to Sep 16 | Arvin Kanan
MY91 | 0077460738 | 10010 | 889227 | Achieva dStream 1.5T - DS | 2024-07-15 | 2024-07-15 | 2024-07-24 | 2024-08-14 | 2024-04-15 | -8 | 4516165105 | HOSPITAL SIBU | PM | Pending PM confirmation | Email follow up sent to PM | Arvin Kanan
MY91 | 0077460738 | 10040 | 889218 | Magnet | 2024-07-15 | (blank) | 2024-07-24 | 2024-08-14 | 2024-05-16 | 16 | 4516165105 | HOSPITAL SIBU | - | > 15 days | > 15 days | Arvin Kanan
MY91 | 0077495838 | 10010 | 782112 | SmartPath to dStream for 1.5T | 2024-07-15 | (blank) | (blank) | (blank) | 2024-05-01 | 5 | 4520129426 | HOSPITAL MIRI | PM | Pending PM confirmation | PM asked to hold the CDD, factory accepted to hold CDD till April end | Arvin Kanan
MY91 | 0077495838 | 10020 | 782300 | RF Coils 1.5T and Biopsy kits | 2024-07-15 | (blank) | (blank) | (blank) | 2024-05-01 | 5 | 4520129426 | HOSPITAL MIRI | PM | Pending PM confirmation | PM asked to hold the CDD, factory accepted to hold CDD till April end | Arvin Kanan
MY91 | 0077498438 | 10010 | 722223 | Azurion 7 M12 | 2024-08-31 | (blank) | (blank) | (blank) | 2024-05-03 | 7 | 4520383573 | SJP Medical Centres Sdn. Bhd. | PM | Pending PM confirmation | Email follow up sent to PM | Yong Kim Loong
MY91 | 0077498438 | 30010 | 722224 | Azurion 7 M20 | 2024-08-31 | (blank) | (blank) | (blank) | 2024-05-02 | 6 | 4520383574 | SJP Medical Centres Sdn. Bhd. | PM | Pending PM confirmation | Email follow up sent to PM | Yong Kim Loong
MY91 | 0077498438 | 30130 | 722467 | Philips Hemo system with IntelliVue X3 | 2024-08-31 | (blank) | (blank) | (blank) | 2024-05-09 | 11 | 4520383574 | SJP Medical Centres Sdn. Bhd. | PM | Pending PM confirmation | Email follow up sent to PM | Yong Kim Loong
MY91 | 0077498438 | 30340 | 722370 | Interfacing with Partners | 2024-08-31 | (blank) | (blank) | (blank) | 2024-05-16 | 16 | 4520383574 | SJP Medical Centres Sdn. Bhd. | - | > 15 days | > 15 days | Yong Kim Loong
PH90 | 6600617239 | 10010 | 722228 | Azurion 5 M20 | 2024-08-20 | 2024-08-01 | 2024-11-04 | 2024-12-02 | 2024-05-03 | 7 | 4518798560 | ROYAL ARC MED SOLUTION CORP. | PM | Pending PM confirmation | Pending with PM | Alonzo Mary Grace
PH90 | 6600617239 | 10090 | 722467 | Philips Hemo system with IntelliVue X3 | 2024-08-20 | (blank) | 2024-11-04 | 2024-12-02 | 2024-05-14 | 14 | 4518798560 | ROYAL ARC MED SOLUTION CORP. | FOM | CCD SWAP | Swap allocation request sent to FOM | Alonzo Mary Grace
PH90 | 6600640055 | 10040 | 881001 | IntelliSpace Portal Solutions | 2025-03-31 | (blank) | 2025-04-01 | 2025-05-30 | 2024-03-20 | -26 | 4519409166 | Lyndon B Johnson | FOM | RDD move out | RDD changed to 31.03.2025; Waiting for revised FSD7 FP | JR., JUN BAXA
PH90 | 6600641387 | 40010 | 728116 | Access CT | 2024-07-01 | 2024-07-01 | 2024-07-02 | 2024-07-29 | 2024-05-06 | 8 | 4519429951 | AIMED ADVANCE IMAGING | PM | Pending PM confirmation | Email follow up sent to PM | JR., JUN BAXA
PH90 | 6600655163 | 10010 | 782110 | MR 5300 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-16 | 2024-05-13 | 13 | 4519744808 | Ilocos Training and Regional | PM | Pending PM confirmation | Email follow up sent to PM | JR., JUN BAXA
PH90 | 6600655163 | 10030 | 782300 | RF Coils 1.5T and Biopsy kits | 2024-08-12 | (blank) | 2024-08-12 | 2024-09-16 | 2024-05-06 | 8 | 4519744808 | Ilocos Training and Regional | PM | Pending PM confirmation | Email follow up sent to PM | JR., JUN BAXA
PH90 | 6600658358 | 20010 | 728116 | Access CT | 2024-06-26 | 2024-06-26 | 2024-06-27 | 2024-07-26 | 2024-04-29 | 3 | 4519847098 | Medcor Dasmariñas Hospital | PM | Pending PM confirmation | Email follow up sent to PM | SANTIAGO GLENN
PH90 | 6600658358 | 20030 | 881030 | IntelliSpace IX/LX Workstations | 2024-06-26 | (blank) | 2024-06-27 | 2024-07-26 | 2024-05-23 | 21 | 4519847102 | Medcor Dasmariñas Hospital | - | > 15 days | > 15 days | SANTIAGO GLENN
PH90 | 6600565081 | 10010 | 722224 | Azurion 7 M20 | 2024-08-30 | 2024-10-28 | 2024-11-06 | 2024-12-13 | 2024-05-14 | 14 | 4517698826 | BASEMED KARE INC. | PM | Pending PM confirmation | Email follow up sent to PM | JR., JUN BAXA
PH90 | 6600565081 | 10090 | 722467 | Philips Hemo system with IntelliVue X3 | 2024-08-30 | (blank) | 2024-11-06 | 2024-12-13 | 2024-05-15 | 15 | 4517698826 | BASEMED KARE INC. | PM | Pending PM confirmation | Email follow up sent to PM | JR., JUN BAXA
PH90 | 6600637912 | 50010 | 782110 | MR 5300 | 2024-08-19 | 2024-08-22 | 2024-08-20 | 2024-09-30 | 2024-05-20 | 18 | 4519329998 | Sto. Tomas Doctors Hospital and Med | - | > 15 days | > 15 days | JR., JUN BAXA
PH90 | 6600637912 | 50030 | 782300 | RF Coils 1.5T and Biopsy kits | 2024-08-19 | (blank) | 2024-08-20 | 2024-09-30 | 2024-05-13 | 13 | 4519329998 | Sto. Tomas Doctors Hospital and Med | PM | Pending PM confirmation | Email follow up sent to PM | JR., JUN BAXA
PH90 | 6600625421 | 10010 | 782110 | MR 5300 | 2024-08-19 | 2024-08-19 | 2024-08-20 | 2024-10-10 | 2024-05-20 | 18 | 4519009690 | Metro IloIlo Hospital | - | > 15 days | > 15 days | SANTIAGO GLENN
PH90 | 6600625421 | 10030 | 782300 | RF Coils 1.5T and Biopsy kits | 2024-08-19 | (blank) | 2024-08-20 | 2024-10-10 | 2024-05-20 | 18 | 4519009690 | Metro IloIlo Hospital | - | > 15 days | > 15 days | SANTIAGO GLENN
PH90 | 6600663027 | 20010 | 881011 | Upgrades IntelliSpace Portal | 2024-07-31 | 2024-06-01 | (blank) | 2024-12-02 | 2024-05-20 | 18 | 4519998841 | ST. LUKE'S MEDICAL CENTER | - | > 15 days | > 15 days | C. Romero
PH90 | 6600663027 | 20020 | 881101 | Advanced Visualization Workspace(881120) | 2024-07-31 | (blank) | (blank) | 2024-12-02 | 2024-05-20 | 18 | 4519998841 | ST. LUKE'S MEDICAL CENTER | - | > 15 days | > 15 days | C. Romero
PH90 | 6600676985 | 10010 | 722228 | Azurion 5 M20 | 2024-08-20 | (blank) | (blank) | 2025-02-24 | 2024-05-22 | 20 | 4520311853 | ROYAL ARC MED SOLUTION CORP. | - | > 15 days | > 15 days | SANTIAGO GLENN
PH90 | 6600676985 | 10090 | 722467 | Philips Hemo system with IntelliVue X3 | 2024-08-20 | (blank) | (blank) | 2025-02-24 | 2024-05-22 | 20 | 4520311853 | ROYAL ARC MED SOLUTION CORP. | - | > 15 days | > 15 days | SANTIAGO GLENN
SG90 | 0006006096 | 10030 | 881101 | Convert IntelliSpace Portal to future | 2021-02-08 | (blank) | (blank) | 2021-09-30 | 2023-12-01 | -104 | 4516069369 | Advanced Medicine Imaging Pte Ltd | PM | Pending PM confirmation | PM to confim on the cancellation | B. Lyn
SG90 | 6600601706 | 10010 | 782107 | Ingenia Elition X | 2024-09-20 | 2023-07-17 | (blank) | 2025-01-30 | 2024-04-19 | -4 | 4518409781 | Precious Medical Centre Pte Ltd | PM | Pending PM confirmation | Cancelled in PSA | Rahmatullah Osman
SG90 | 6600601706 | 10040 | 782301 | RF Coils 3.0T and Biopsy kits | 2024-09-20 | (blank) | (blank) | 2025-01-30 | 2024-04-19 | -4 | 4518409781 | Precious Medical Centre Pte Ltd | PM | Pending PM confirmation | Cancelled in PSA | Rahmatullah Osman
SG90 | 6600655154 | 10010 | 782109 | Ingenia Ambition X | 2024-06-25 | 2024-06-25 | 2024-06-27 | 2024-09-25 | 2024-04-26 | 2 | 4519744009 | Sind Institute of Urology And | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness | Arvin Kanan
SG90 | 6600655154 | 10030 | 782300 | RF Coils 1.5T and Biopsy kits | 2024-06-25 | (blank) | 2024-06-27 | 2024-09-25 | 2024-04-26 | 2 | 4519744009 | Sind Institute of Urology And | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness | Arvin Kanan
SG90 | 6600655154 | 10020 | 781322 | MR Elastography | 2024-06-25 | (blank) | 2024-06-27 | 2024-09-25 | 2024-05-14 | 14 | 4519744009 | Sind Institute of Urology And | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness | Arvin Kanan
SG90 | 6600655154 | 10040 | 782409 | Magnet Ingenia Ambition X | 2024-06-25 | (blank) | 2024-06-27 | 2024-09-25 | 2024-04-26 | 2 | 4519744009 | Sind Institute of Urology And | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness | Arvin Kanan
SG90 | 6600676701 | 20040 | 712084 | DigitalDiagnost Upgrades | 2024-06-01 | (blank) | (blank) | (blank) | 2024-05-02 | 6 | 4520297821 | Alexandra Health Pte Ltd | PM | Pending PM confirmation | Issue in PSA to set Z4 fromPM | Valence Wong
SG90 | 6600677257 | 10010 | 718133 | Zenition 70 | 2024-06-15 | (blank) | (blank) | (blank) | 2024-05-08 | 10 | 4520308246 | Gleneagles Hospital Ltd | FOM | Material Hold in factory | Product under RA Labelling hold, till date no firm CDD. | Norzhar BinSalim
SG90 | 6600680937 | 10010 | 728272 | Upgrd Brilliance CT Big Bore | 2024-06-10 | (blank) | (blank) | (blank) | 2024-04-24 | 0 | 4520373907 | Mount Elizabeth Hospital | #N/A | #N/A | #N/A | No Project Manager
SG90 | 6600680937 | 10030 | 870240 | TumorLOC Server | 2024-05-27 | (blank) | (blank) | (blank) | 2024-04-26 | 2 | 4520373908 | Mount Elizabeth Hospital | #N/A | #N/A | #N/A | No Project Manager
SG90 | 6600680937 | 10020 | 870227 | P16.2.1 Tumor LOC | 2024-05-27 | (blank) | (blank) | (blank) | 2024-04-26 | 2 | 4520373908 | Mount Elizabeth Hospital | #N/A | #N/A | #N/A | No Project Manager
SG90 | 6600678065 | 20010 | 888121 | Ambient Experience | 2024-06-01 | 2024-07-04 | 2024-07-12 | (blank) | 2024-05-24 | 22 | 4520320088 | National University Hospital | - | > 15 days | > 15 days | Mr Hanko Bintoro
SG90 | 6600683112 | 10010 | 722141 | Technology Maximizer Allura | 2024-05-21 | (blank) | (blank) | (blank) | 2024-04-23 | -2 | 4520397385 | National Heart Centre of Singapore | #N/A | #N/A | #N/A | Ram Vinna R
TH90 | 6600588073 | 10010 | 722224 | Azurion 7 M20 | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-05-23 | 2024-04-07 | -13 | 4518055124 | SICHON HOSPITAL | PM | Pending PM confirmation | Pending with PM; Planning to swap | Photichanprasert Wimolphan
TH90 | 6600588073 | 10090 | 722467 | Philips Hemo system with IntelliVue X3 | 2025-04-21 | (blank) | 2025-04-21 | 2025-05-23 | 2024-04-14 | -8 | 4518055124 | SICHON HOSPITAL | PM | Pending PM confirmation | Pending with PM; Planning to swap | Photichanprasert Wimolphan
TH90 | 6600660454 | 10010 | 722225 | Azurion 7 B12 | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-10-25 | 2024-04-20 | -3 | 4519906302 | ROYAL THAI AIR FORCE HOSPITAL | PM | Pending PM confirmation | Pending with PM | Photichanprasert Wimolphan
TH90 | 6600660454 | 10100 | 722467 | Philips Hemo system with IntelliVue X3 | 2024-09-13 | (blank) | 2024-09-13 | 2024-10-25 | 2024-05-19 | 17 | 4519906302 | ROYAL THAI AIR FORCE HOSPITAL | - | > 15 days | > 15 days | Photichanprasert Wimolphan
TH90 | 6600678888 | 10010 | 722227 | Azurion 5 M12 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2024-11-08 | 2024-04-16 | -7 | 4520330249 | Loei Hospital | PM | Pending PM confirmation | Pending with PM | Photichanprasert Wimolphan
TH90 | 6600678888 | 10090 | 722467 | Philips Hemo system with IntelliVue X3 | 2024-10-03 | (blank) | 2024-10-03 | 2024-11-08 | 2024-04-16 | -7 | 4520330249 | Loei Hospital | PM | Pending PM confirmation | Pending with PM | Photichanprasert Wimolphan
TH90 | 6600629397 | 10010 | 782110 | MR 5300 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-09-13 | 2024-05-06 | 8 | 4519125383 | CHOPHAYA ABHAIBHUBEJHR HOSPITAL | PM | Pending PM confirmation | Email follow up sent to PM | Photichanprasert Wimolphan
TH90 | 6600629397 | 10030 | 782300 | RF Coils 1.5T and Biopsy kits | 2024-08-07 | (blank) | 2024-08-07 | 2024-09-13 | 2024-05-06 | 8 | 4519125383 | CHOPHAYA ABHAIBHUBEJHR HOSPITAL | PM | Pending PM confirmation | Email follow up sent to PM | Photichanprasert Wimolphan
TH90 | 6600664230 | 40010 | 728144 | Incisive CT | 2024-10-04 | 2024-07-04 | 2024-07-04 | 2024-09-27 | 2024-05-07 | 9 | 4520018443 | M.I.CALIBRATION SYSTEM CO., LTD. | PM | Pending PM confirmation | Email follow up sent to PM | Photichanprasert Wimolphan
TH90 | 6600679508 | 30010 | 728327 | Upgrades Ingenuity CT | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-11-29 | 2024-04-29 | 3 | 4520332131 | SIKARIN CO., LTD. | PM | Pending PM confirmation | Email follow up sent to PM | Janthong Wischa
TH90 | 6600566479 | 50010 | 718096 | Zenition 50 | 2024-07-05 | 2024-07-05 | 2024-07-05 | 2024-07-31 | 2024-05-22 | 20 | 4517539683 | KP5 CO., LTD. | - | > 15 days | > 15 days | Samutdontri Supawadee
TH90 | 6600622442 | 40010 | 722136 | Field Extensions Azurion 7 | 2024-04-20 | (blank) | 2024-05-30 | 2024-06-21 | 2024-04-01 | -18 | 4520345090 | FORT WACHIRAWUT HOSPITAL | #N/A | #N/A | #N/A | Photichanprasert Wimolphan
TH90 | 6600664231 | 10010 | 722226 | Azurion 7 B20 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2024-11-08 | 2024-05-24 | 22 | 4520018521 | RAMKHAMHAENG HOSPITAL | - | > 15 days | > 15 days | Photichanprasert Wimolphan
VN90 | 6600661158 | 10010 | 881001 | IntelliSpace Portal Solutions | 2024-06-14 | 2024-06-14 | 2024-06-17 | 2025-07-21 | 2024-05-09 | 11 | 4519957015 | HCM HEART INSTITUDE | PM | RDD move out | PM to confirm on the dates. | NGUYEN HUU TAI
VN90 | 6600661158 | 10040 | 881101 | Advanced Visualization Workspace(881120) | 2024-06-14 | (blank) | 2024-06-17 | 2025-07-21 | 2024-04-09 | -12 | 4519957015 | HCM HEART INSTITUDE | FOM | RDD move out | Not relvant for Z4 | NGUYEN HUU TAI
VN90 | 6600679090 | 10010 | 722224 | Azurion 7 M20 | 2024-07-26 | 2024-08-05 | (blank) | 2024-10-14 | 2024-05-14 | 14 | 4520382600 | Thien Hanh General Hospital | PM | RDD move out | PM to confirm on the dates. | NGUYEN HUU TAI
VN90 | 6600679090 | 10090 | 722467 | Philips Hemo system with IntelliVue X3 | 2024-07-26 | (blank) | (blank) | 2024-10-14 | 2024-05-14 | 14 | 4520382600 | Thien Hanh General Hospital | PM | RDD move out | PM to confirm on the dates. | NGUYEN HUU TAI
VN90 | 6600678936 | 10010 | 728144 | Incisive CT | 2024-07-18 | 2024-07-18 | (blank) | 2024-10-04 | 2024-05-13 | 13 | 4520383262 | An Sinh Hospital | PM | RDD move out | PM to confirm on the dates. | Le Ba Tan
NZ90 | 6600677975 | 10100 | 782142 | Upgrades dStream to R11 | 2024-05-12 | 2024-05-06 | 2024-05-06 | 2024-05-13 | 2024-04-26 | 2 | 4520327150 | NORTH SHORE HOSPITAL | PM | Pending PM confirmation | Email follow up sent to PM | Kate Wackrow
NZ90 | 6600677975 | 10200 | 781126 | SmartSpeed AI | 2024-05-12 | (blank) | 2024-05-06 | 2024-05-13 | 2024-04-26 | 2 | 4520327150 | NORTH SHORE HOSPITAL | PM | Pending PM confirmation | Email follow up sent to PM | Kate Wackrow
NZ90 | 6600677975 | 10300 | 781334 | ICAP AV | 2024-05-12 | (blank) | 2024-05-06 | 2024-05-13 | 2024-04-26 | 2 | 4520327150 | NORTH SHORE HOSPITAL | PM | Pending PM confirmation | Email follow up sent to PM | Kate Wackrow
NZ90 | 6600678199 | 10100 | 712034 | DigitalDiagnost C90 High Performance | 2024-07-08 | (blank) | (blank) | 2024-08-07 | 2024-05-07 | 9 | 4520327446 | TRG Imaging Ltd | PM | Pending PM confirmation | Email follow up sent to PM | Kate Wackrow
NZ90 | 6600674706 | 10010 | 782142 | Upgrades dStream to R11 | 2024-04-09 | (blank) | (blank) | 2024-06-28 | 2024-04-26 | 2 | 4520255389 | Southland Hospital | PM | Pending PM confirmation | Email follow up sent to PM | Kate Wackrow
NZ90 | 6600674706 | 10020 | 781334 | ICAP AV | 2024-04-09 | (blank) | (blank) | 2024-06-28 | 2024-04-26 | 2 | 4520255389 | Southland Hospital | PM | Pending PM confirmation | Email follow up sent to PM | Kate Wackrow
NZ90 | 6600680321 | 10100 | 712034 | DigitalDiagnost C90 High Performance | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-08-09 | 2024-05-21 | 19 | 4520356889 | TOKOROA HOSPITAL | - | > 15 days | > 15 days | Kate Wackrow
Grand Total
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Data
Sales Document | SO Item | PO Number | PO Item | Ship to Customer Name | Material | Material Description | Sales Org | Market OM | Project Manager | FSR | AB Confirmation | Start Frozen Period Date | Z4OK | Z3 | SID | CAD | PMRDD | RDD | Z4 Status | INCP | BG Name | Days until Start FP | Ref | Owner | Comments - High | Detialed Comments
6600565081 | 10010 | 4517698826 | 10 | BASEMED KARE INC. | 722224 | Azurion 7 M20 | PH90 | Charan GS | JR., JUN BAXA | 2024-06-24 | 2024-08-30 | 2024-05-14 | (blank) | 2022-04-06 | 2024-11-06 | 2024-12-13 | 2024-10-28 | 2024-08-30 | Z4 Frozen <15days | No | IGT-S | 1 | 660056508110010 | PM | Pending PM confirmation | Email follow up sent to PM
6600565081 | 10090 | 4517698826 | 90 | BASEMED KARE INC. | 722467 | Philips Hemo system with IntelliVue X3 | PH90 | Charan GS | JR., JUN BAXA | 2024-06-24 | 2024-08-30 | 2024-05-15 | (blank) | 2022-08-10 | 2024-11-06 | 2024-12-13 | (blank) | 2024-08-30 | Z4 Frozen <15days | No | IGT-S | 2 | 660056508110090 | PM | Pending PM confirmation | Email follow up sent to PM
6600566479 | 50010 | 4517539683 | 10 | KP5 CO., LTD. | 718096 | Zenition 50 | TH90 | Charan GS | Samutdontri Supawadee | 2023-10-16 | 2024-07-05 | 2024-05-22 | (blank) | 2023-01-11 | 2024-07-05 | 2024-07-31 | 2024-07-05 | 2024-07-05 | Z4 Frozen <30days | No | IGT-S | 7 | 660056647950010 | - | > 15 days | > 15 days
6600588073 | 10010 | 4518055124 | 10 | SICHON HOSPITAL | 722224 | Azurion 7 M20 | TH90 | Charan GS | Photichanprasert Wimolphan | 2025-04-21 | 2024-08-12 | 2024-04-07 | (blank) | 2023-10-17 | 2025-04-21 | 2025-05-23 | 2025-04-21 | 2025-04-21 | Z4 Frozen - Past | No | IGT-S | -26 | 660058807310010 | PM | Pending PM confirmation | Pending with PM; Planning to swap
6600588073 | 10090 | 4518055124 | 90 | SICHON HOSPITAL | 722467 | Philips Hemo system with IntelliVue X3 | TH90 | Charan GS | Photichanprasert Wimolphan | 2025-04-21 | 2024-08-12 | 2024-04-14 | (blank) | 2023-10-17 | 2025-04-21 | 2025-05-23 | (blank) | 2025-04-21 | Z4 Frozen - Past | No | IGT-S | -21 | 660058807310090 | PM | Pending PM confirmation | Pending with PM; Planning to swap
6600601706 | 10010 | 4518409781 | 10 | Precious Medical Centre Pte Ltd | 782107 | Ingenia Elition X | SG90 | Ram Vinna R | Rahmatullah Osman | 2025-01-30 | 2024-07-17 | 2024-04-19 | (blank) | 2024-04-04 | (blank) | 2025-01-30 | 2023-07-17 | 2024-09-20 | Z4 Frozen - Past | Yes | MR OEM | -17 | 660060170610010 | PM | Pending PM confirmation | Cancelled in PSA
6600601706 | 10040 | 4518409781 | 40 | Precious Medical Centre Pte Ltd | 782301 | RF Coils 3.0T and Biopsy kits | SG90 | Ram Vinna R | Rahmatullah Osman | 2025-01-30 | 2024-07-17 | 2024-04-19 | (blank) | 2024-04-04 | (blank) | 2025-01-30 | (blank) | 2024-09-20 | Z4 Frozen - Past | Yes | MR OEM | -17 | 660060170610040 | PM | Pending PM confirmation | Cancelled in PSA
6600617239 | 10010 | 4518798560 | 10 | ROYAL ARC MED SOLUTION CORP. | 722228 | Azurion 5 M20 | PH90 | Charan GS | Alonzo Mary Grace | 2024-08-20 | 2024-08-20 | 2024-05-03 | (blank) | 2023-08-25 | 2024-11-04 | 2024-12-02 | 2024-08-01 | 2024-08-20 | Z4 Frozen <15days | No | IGT-S | -7 | 660061723910010 | PM | Pending PM confirmation | Pending with PM
6600617239 | 10090 | 4518798560 | 90 | ROYAL ARC MED SOLUTION CORP. | 722467 | Philips Hemo system with IntelliVue X3 | PH90 | Charan GS | Alonzo Mary Grace | 2024-08-20 | 2024-08-20 | 2024-05-14 | (blank) | 2023-08-25 | 2024-11-04 | 2024-12-02 | (blank) | 2024-08-20 | Z4 Frozen <15days | No | IGT-S | 1 | 660061723910090 | FOM | CCD SWAP | Swap allocation request sent to FOM
6600617503 | 10010 | 4518796283 | 10 | Royal North Shore Hospital | 722226 | Azurion 7 B20 | AU90 | V Thirumalesh | Fernandez Jaz | 2023-05-15 | 2024-08-27 | 2024-04-23 | (blank) | 2023-02-16 | 2024-11-01 | 2024-12-13 | 2024-11-01 | 2024-11-01 | Z4 Frozen - Past | No | IGT-S | -15 | 660061750310010 | FOM | RDD move out | RDD move out- revised FPD required
6600617503 | 10110 | 4518796283 | 90 | Royal North Shore Hospital | 722367 | DoseAware | AU90 | V Thirumalesh | Fernandez Jaz | 2023-05-15 | 2024-08-27 | 2024-04-28 | (blank) | 2023-02-16 | 2024-11-01 | 2024-12-13 | (blank) | 2024-11-01 | Z4 Frozen <15days | No | IGT-S | -11 | 660061750310110 | PM | Pending PM confirmation | Email follow up sent to PM
6600622442 | 40010 | 4520345090 | 10 | FORT WACHIRAWUT HOSPITAL | 722136 | Field Extensions Azurion 7 | TH90 | Charan GS | Photichanprasert Wimolphan | 2024-04-22 | 2024-05-13 | 2024-04-01 | (blank) | 2024-04-09 | 2024-05-30 | 2024-06-21 | (blank) | 2024-04-20 | Z4 Frozen - Past | No | PD Other | -31 | 660062244240010 | #N/A | #N/A | #N/A
6600625421 | 10010 | 4519009690 | 10 | Metro IloIlo Hospital | 782110 | MR 5300 | PH90 | Charan GS | SANTIAGO GLENN | 2024-03-29 | 2024-08-19 | 2024-05-20 | (blank) | 2024-03-10 | 2024-08-20 | 2024-10-10 | 2024-08-19 | 2024-08-19 | Z4 Frozen <30days | No | MR OEM | 5 | 660062542110010 | - | > 15 days | > 15 days
6600625421 | 10030 | 4519009690 | 30 | Metro IloIlo Hospital | 782300 | RF Coils 1.5T and Biopsy kits | PH90 | Charan GS | SANTIAGO GLENN | 2024-03-29 | 2024-08-19 | 2024-05-20 | (blank) | 2024-03-10 | 2024-08-20 | 2024-10-10 | (blank) | 2024-08-19 | Z4 Frozen <30days | No | MR OEM | 5 | 660062542110030 | - | > 15 days | > 15 days
6600629397 | 10010 | 4519125383 | 10 | CHOPHAYA ABHAIBHUBEJHR HOSPITAL | 782110 | MR 5300 | TH90 | Charan GS | Photichanprasert Wimolphan | 2024-08-07 | 2024-08-07 | 2024-05-06 | (blank) | 2024-04-21 | 2024-08-07 | 2024-09-13 | 2024-08-07 | 2024-08-07 | Z4 Frozen <15days | No | MR OEM | -6 | 660062939710010 | PM | Pending PM confirmation | Email follow up sent to PM
6600629397 | 10030 | 4519125383 | 30 | CHOPHAYA ABHAIBHUBEJHR HOSPITAL | 782300 | RF Coils 1.5T and Biopsy kits | TH90 | Charan GS | Photichanprasert Wimolphan | 2024-08-07 | 2024-08-07 | 2024-05-06 | (blank) | 2024-04-21 | 2024-08-07 | 2024-09-13 | (blank) | 2024-08-07 | Z4 Frozen <15days | No | MR OEM | -6 | 660062939710030 | PM | Pending PM confirmation | Email follow up sent to PM
6600633483 | 10010 | 4519205405 | 10 | M&H | 728144 | Incisive CT | KR90 | MOON HOSUAH | LEE YH | 2024-06-28 | 2024-06-28 | 2024-05-06 | (blank) | 2024-01-30 | 2024-08-01 | 2024-08-30 | 2023-11-30 | 2024-06-28 | Z4 Frozen <15days | No | CT AMI | -6 | 660063348310010 | PM | Pending PM confirmation | Pending Z4OK approval from PM
6600633483 | 30010 | 4519989707 | 10 | M&H | 881030 | IntelliSpace IX/LX Workstations | KR90 | MOON HOSUAH | LEE YH | 2024-06-28 | 2024-06-28 | 2024-05-24 | (blank) | (blank) | 2024-08-01 | 2024-08-30 | (blank) | 2024-06-28 | Z4 Frozen <30days | No | Clinical Informatics | 9 | 660063348330010 | - | > 15 days | > 15 days
6600637628 | 20010 | 4520206916 | 10 | PERTH RADIOLOGICAL CLINIC-SUBIACO | 881101 | Advanced Visualization Workspace(881120) | AU90 | Meliza VIda | Sabrina Censi | 2023-09-15 | 2024-06-10 | 2024-05-01 | (blank) | (blank) | (blank) | 2024-06-30 | (blank) | 2024-06-13 | Z4 Frozen <15days | No | Clinical Informatics | -9 | 660063762820010 | PM | Pending PM confirmation | Email follow up sent to PM
6600637912 | 50010 | 4519329998 | 10 | Sto. Tomas Doctors Hospital and Med | 782110 | MR 5300 | PH90 | Charan GS | JR., JUN BAXA | 2024-05-30 | 2024-08-19 | 2024-05-20 | (blank) | 2024-01-14 | 2024-08-20 | 2024-09-30 | 2024-08-22 | 2024-08-19 | Z4 Frozen <30days | No | MR OEM | 5 | 660063791250010 | - | > 15 days | > 15 days
6600637912 | 50030 | 4519329998 | 30 | Sto. Tomas Doctors Hospital and Med | 782300 | RF Coils 1.5T and Biopsy kits | PH90 | Charan GS | JR., JUN BAXA | 2024-05-30 | 2024-08-19 | 2024-05-13 | (blank) | 2024-01-14 | 2024-08-20 | 2024-09-30 | (blank) | 2024-08-19 | Z4 Frozen <15days | No | MR OEM | 0 | 660063791250030 | PM | Pending PM confirmation | Email follow up sent to PM
6600640055 | 10040 | 4519409166 | 10 | Lyndon B Johnson | 881001 | IntelliSpace Portal Solutions | PH90 | Charan GS | JR., JUN BAXA | 2024-10-14 | 2025-03-31 | 2024-03-20 | (blank) | 2024-03-19 | 2025-04-01 | 2025-05-30 | (blank) | 2025-03-31 | Z4 Frozen - Past | No | Clinical Informatics | -39 | 660064005510040 | FOM | RDD move out | RDD changed to 31.03.2025; Waiting for revised FSD7 FP
6600642439 | 10010 | (blank) | (blank) | KOREA UNIV.HOSP.ANSAN | 718075 | BV Endura R2.3 | KR90 | MOON HOSUAH | LIM CS | 2025-03-30 | - | 2024-02-20 | (blank) | 2023-09-06 | 2025-03-30 | 2025-04-30 | 2024-03-30 | 2025-03-30 | Z4 Frozen - Past | No | IGT-S | -60 | 660064243910010 | PM | Pending PM confirmation | Order to be debooked by end of April
6600641987 | 10010 | 4519433563 | 10 | Sokcho Medical Center | 728144 | Incisive CT | KR90 | MOON HOSUAH | LEE YH | 2024-07-30 | 2024-07-30 | 2024-05-09 | (blank) | 2023-12-20 | 2024-08-19 | 2024-09-27 | 2024-07-30 | 2024-07-30 | Z4 Frozen <15days | No | CT AMI | -3 | 660064198710010 | PM | Pending PM confirmation | Pending Z4OK approval from PM
6600641387 | 40010 | 4519429951 | 10 | AIMED ADVANCE IMAGING | 728116 | Access CT | PH90 | Charan GS | JR., JUN BAXA | 2024-05-30 | 2024-07-01 | 2024-05-06 | (blank) | 2024-04-15 | 2024-07-02 | 2024-07-29 | 2024-07-01 | 2024-07-01 | Z4 Frozen <15days | No | CT AMI | -6 | 660064138740010 | PM | Pending PM confirmation | Email follow up sent to PM
6600642984 | 10010 | 4519469397 | 10 | Wyvern Health Pty Ltd | 718133 | Zenition 70 | AU90 | Meliza VIda | Christine Suriyarachchi | 2024-07-02 | 2024-07-02 | 2024-05-23 | (blank) | 2024-01-31 | 2024-07-15 | 2024-07-30 | 2024-07-05 | 2024-07-02 | Z4 Frozen <30days | No | IGT-S | 8 | 660064298410010 | - | > 15 days | > 15 days
6600642984 | 20010 | 4519469398 | 10 | Wyvern Health Pty Ltd | 718133 | Zenition 70 | AU90 | Meliza VIda | Christine Suriyarachchi | 2024-07-02 | 2024-07-02 | 2024-05-24 | (blank) | 2024-02-01 | 2024-07-15 | 2024-07-30 | 2024-07-05 | 2024-07-02 | Z4 Frozen <30days | No | IGT-S | 9 | 660064298420010 | - | > 15 days | > 15 days
6600654259 | 10010 | 4519734315 | 10 | GOLD COAST UNIVERSITY HOSPITAL | 722226 | Azurion 7 B20 | AU90 | Meliza VIda | Croft Tom | 2024-02-09 | 2024-09-23 | 2024-05-24 | (blank) | 2023-10-29 | 2024-10-07 | 2024-11-28 | 2024-10-06 | 2024-10-06 | Z4 Frozen <30days | No | IGT-S | 9 | 660065425910010 | FOM | RDD move out | RDD move out- revised FPD required
6600655163 | 10010 | 4519744808 | 10 | Ilocos Training and Regional | 782110 | MR 5300 | PH90 | Charan GS | JR., JUN BAXA | 2024-08-12 | 2024-08-12 | 2024-05-13 | (blank) | (blank) | 2024-08-12 | 2024-09-16 | 2024-08-12 | 2024-08-12 | Z4 Frozen <15days | No | MR OEM | 0 | 660065516310010 | PM | Pending PM confirmation | Email follow up sent to PM
6600655163 | 10030 | 4519744808 | 30 | Ilocos Training and Regional | 782300 | RF Coils 1.5T and Biopsy kits | PH90 | Charan GS | JR., JUN BAXA | 2024-08-12 | 2024-08-12 | 2024-05-06 | (blank) | 2024-04-21 | 2024-08-12 | 2024-09-16 | (blank) | 2024-08-12 | Z4 Frozen <15days | No | MR OEM | -6 | 660065516310030 | PM | Pending PM confirmation | Email follow up sent to PM
6600655154 | 10010 | 4519744009 | 10 | Sind Institute of Urology And | 782109 | Ingenia Ambition X | SG90 | Ram Vinna R | Arvin Kanan | 2024-06-25 | 2024-06-25 | 2024-04-26 | (blank) | 2024-02-27 | 2024-06-27 | 2024-09-25 | 2024-06-25 | 2024-06-25 | Z4 Frozen <15days | No | MR OEM | -12 | 660065515410010 | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness
6600655154 | 10020 | 4519744009 | 20 | Sind Institute of Urology And | 781322 | MR Elastography | SG90 | Ram Vinna R | Arvin Kanan | 2024-06-25 | 2024-06-25 | 2024-05-14 | (blank) | 2024-04-16 | 2024-06-27 | 2024-09-25 | (blank) | 2024-06-25 | Z4 Frozen <15days | No | MR OEM | 1 | 660065515410020 | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness
6600655154 | 10030 | 4519744009 | 30 | Sind Institute of Urology And | 782300 | RF Coils 1.5T and Biopsy kits | SG90 | Ram Vinna R | Arvin Kanan | 2024-06-25 | 2024-06-25 | 2024-04-26 | (blank) | 2024-02-27 | 2024-06-27 | 2024-09-25 | (blank) | 2024-06-25 | Z4 Frozen <15days | No | MR OEM | -12 | 660065515410030 | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness
6600655154 | 10040 | 4519744009 | 40 | Sind Institute of Urology And | 782409 | Magnet Ingenia Ambition X | SG90 | Ram Vinna R | Arvin Kanan | 2024-06-25 | 2024-06-25 | 2024-04-26 | (blank) | 2024-02-27 | 2024-06-27 | 2024-09-25 | (blank) | 2024-06-25 | Z4 Frozen <15days | No | MR OEM | -12 | 660065515410040 | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness
6600658358 | 20010 | 4519847098 | 10 | Medcor Dasmariñas Hospital | 728116 | Access CT | PH90 | Charan GS | SANTIAGO GLENN | 2024-05-14 | 2024-06-26 | 2024-04-29 | (blank) | 2024-01-09 | 2024-06-27 | 2024-07-26 | 2024-06-26 | 2024-06-26 | Z4 Frozen <15days | No | CT AMI | -11 | 660065835820010 | PM | Pending PM confirmation | Email follow up sent to PM
6600658358 | 20030 | 4519847102 | 10 | Medcor Dasmariñas Hospital | 881030 | IntelliSpace IX/LX Workstations | PH90 | Charan GS | SANTIAGO GLENN | 2024-05-14 | 2024-06-26 | 2024-05-23 | (blank) | (blank) | 2024-06-27 | 2024-07-26 | (blank) | 2024-06-26 | Z4 Frozen <30days | No | Clinical Informatics | 8 | 660065835820030 | - | > 15 days | > 15 days
6600660454 | 10010 | 4519906302 | 10 | ROYAL THAI AIR FORCE HOSPITAL | 722225 | Azurion 7 B12 | TH90 | Charan GS | Photichanprasert Wimolphan | 2024-05-30 | 2024-08-19 | 2024-04-20 | (blank) | 2023-12-01 | 2024-09-13 | 2024-10-25 | 2024-09-13 | 2024-09-13 | Z4 Frozen - Past | No | IGT-S | -16 | 660066045410010 | PM | Pending PM confirmation | Pending with PM
6600660454 | 10100 | 4519906302 | 100 | ROYAL THAI AIR FORCE HOSPITAL | 722467 | Philips Hemo system with IntelliVue X3 | TH90 | Charan GS | Photichanprasert Wimolphan | 2024-05-30 | 2024-08-19 | 2024-05-19 | (blank) | (blank) | 2024-09-13 | 2024-10-25 | (blank) | 2024-09-13 | Z4 Frozen <30days | No | IGT-S | 4 | 660066045410100 | - | > 15 days | > 15 days
6600661158 | 10010 | 4519957015 | 10 | HCM HEART INSTITUDE | 881001 | IntelliSpace Portal Solutions | VN90 | Arun Kumar | NGUYEN HUU TAI | 2024-05-15 | 2024-06-14 | 2024-05-09 | (blank) | (blank) | 2024-06-17 | 2025-07-21 | 2024-06-14 | 2024-06-14 | Z4 Frozen <15days | No | Clinical Informatics | -3 | 660066115810010 | PM | RDD move out | PM to confirm on the dates.
6600661158 | 10040 | 4519957015 | 30 | HCM HEART INSTITUDE | 881101 | Advanced Visualization Workspace(881120) | VN90 | Arun Kumar | NGUYEN HUU TAI | 2024-05-15 | 2024-05-15 | 2024-04-09 | (blank) | (blank) | 2024-06-17 | 2025-07-21 | (blank) | 2024-06-14 | Z4 Frozen - Past | No | Clinical Informatics | -25 | 660066115810040 | FOM | RDD move out | Not relvant for Z4
6600662625 | 10010 | 4519960023 | 10 | IA Corporation Pty Ltd | 712035 | DigitalDiagnost C90 Flex/Value/Chest/ER | AU90 | Meliza VIda | Peter Bestawrose | 2024-07-29 | 2024-07-24 | 2024-05-17 | (blank) | (blank) | 2024-08-12 | 2024-09-06 | 2024-07-30 | 2024-07-29 | Z4 Frozen <30days | No | DXR | 4 | 660066262510010 | - | > 15 days | > 15 days
6600662625 | 80010 | 4519960020 | 10 | IA Corporation Pty Ltd | 728144 | Incisive CT | AU90 | Meliza VIda | Peter Bestawrose | 2024-07-29 | 2024-07-25 | 2024-05-17 | (blank) | (blank) | 2024-08-12 | 2024-09-06 | 2024-07-30 | 2024-07-29 | Z4 Frozen <30days | No | CT AMI | 4 | 660066262580010 | - | > 15 days | > 15 days
6600663027 | 20010 | 4519998841 | 10 | ST. LUKE'S MEDICAL CENTER | 881011 | Upgrades IntelliSpace Portal | PH90 | Charan GS | C. Romero | 2024-12-31 | 2024-07-31 | 2024-05-20 | (blank) | 2023-12-17 | (blank) | 2024-12-02 | 2024-06-01 | 2024-07-31 | Z4 Frozen <30days | No | Clinical Informatics | 5 | 660066302720010 | - | > 15 days | > 15 days
6600663027 | 20020 | 4519998841 | 20 | ST. LUKE'S MEDICAL CENTER | 881101 | Advanced Visualization Workspace(881120) | PH90 | Charan GS | C. Romero | 2024-12-31 | 2024-07-31 | 2024-05-20 | (blank) | (blank) | (blank) | 2024-12-02 | (blank) | 2024-07-31 | Z4 Frozen <30days | No | Clinical Informatics | 5 | 660066302720020 | - | > 15 days | > 15 days
6600664231 | 10010 | 4520018521 | 10 | RAMKHAMHAENG HOSPITAL | 722226 | Azurion 7 B20 | TH90 | Charan GS | Photichanprasert Wimolphan | 2024-10-10 | 2024-10-03 | 2024-05-24 | (blank) | (blank) | 2024-10-03 | 2024-11-08 | 2024-10-03 | 2024-10-03 | Z4 Frozen <30days | No | IGT-S | 9 | 660066423110010 | - | > 15 days | > 15 days
6600664230 | 40010 | 4520018443 | 10 | M.I.CALIBRATION SYSTEM CO., LTD. | 728144 | Incisive CT | TH90 | Charan GS | Photichanprasert Wimolphan | 2024-06-30 | 2024-07-04 | 2024-05-07 | (blank) | 2023-12-28 | 2024-07-04 | 2024-09-27 | 2024-07-04 | 2024-10-04 | Z4 Frozen <15days | No | CT AMI | -5 | 660066423040010 | PM | Pending PM confirmation | Email follow up sent to PM
6600669039 | 10010 | 4520140639 | 10 | Royal North Shore Hospital | 722226 | Azurion 7 B20 | AU90 | Meliza VIda | Fernandez Jaz | 2024-06-01 | 2024-08-26 | 2024-04-23 | (blank) | 2024-02-12 | 2024-09-16 | 2024-10-25 | 2024-09-15 | 2024-09-15 | Z4 Frozen - Past | Yes | IGT-S | -15 | 660066903910010 | FOM | RDD move out | RDD move out- revised FPD required
6600673703 | 20010 | 4520236074 | 10 | Chonnam National University | 722137 | Field Extensions Azurion 5 | KR90 | MOON HOSUAH | LEE YH | 2024-06-28 | 2024-06-28 | 2024-05-16 | (blank) | (blank) | 2024-06-28 | 2024-08-30 | 2024-06-28 | 2024-06-28 | Z4 Frozen <30days | No | IGT-S | 3 | 660067370320010 | - | > 15 days | > 15 days
6600673265 | 20100 | 4520242547 | 10 | RADIOLOGYSA SERVICE TRUST | 718133 | Zenition 70 | AU90 | V Thirumalesh | Ting David | 2024-05-06 | 2024-07-02 | 2024-05-21 | (blank) | (blank) | 2024-07-15 | 2024-07-19 | 2024-07-05 | 2024-07-05 | Z4 Frozen <30days | No | IGT-S | 6 | 660067326520100 | - | > 15 days | > 15 days
6600674706 | 10010 | 4520255389 | 10 | Southland Hospital | 782142 | Upgrades dStream to R11 | NZ90 | V Thirumalesh | Kate Wackrow | 2024-04-09 | 2024-05-30 | 2024-04-26 | (blank) | 2024-04-11 | (blank) | 2024-06-28 | (blank) | 2024-04-09 | Z4 Frozen <15days | No | MR OEM | -12 | 660067470610010 | PM | Pending PM confirmation | Email follow up sent to PM
6600674706 | 10020 | 4520255389 | 20 | Southland Hospital | 781334 | ICAP AV | NZ90 | V Thirumalesh | Kate Wackrow | 2024-04-09 | 2024-05-30 | 2024-04-26 | (blank) | (blank) | (blank) | 2024-06-28 | (blank) | 2024-04-09 | Z4 Frozen <15days | No | Clinical Informatics | -12 | 660067470610020 | PM | Pending PM confirmation | Email follow up sent to PM
6600674385 | 10010 | 4520280924 | 10 | RSUD Taman Husada | 718096 | Zenition 50 | ID90 | Arun Kumar | Mr Rivaldo Sutanto Felix | 2024-07-01 | 2024-07-01 | 2024-05-17 | (blank) | (blank) | 2024-07-02 | 2024-08-09 | 2024-07-01 | 2024-07-01 | Z4 Frozen <30days | No | IGT-S | 4 | 660067438510010 | - | > 15 days | > 15 days
6600676701 | 20040 | 4520297821 | 10 | Alexandra Health Pte Ltd | 712084 | DigitalDiagnost Upgrades | SG90 | Ram Vinna R | Valence Wong | 2024-03-18 | 2024-05-31 | 2024-05-02 | (blank) | 2024-04-17 | (blank) | (blank) | (blank) | 2024-06-01 | Z4 Frozen <15days | No | PD Other | -8 | 660067670120040 | PM | Pending PM confirmation | Issue in PSA to set Z4 fromPM
6600676407 | 10010 | 4520292932 | 10 | RSAU Lanud Sulaiman | 728144 | Incisive CT | ID90 | Arun Kumar | Mr Rivaldo Sutanto Felix | 2024-08-20 | 2024-08-20 | 2024-05-10 | (blank) | (blank) | (blank) | 2024-09-20 | 2024-08-20 | 2024-08-20 | Z4 Frozen <15days | No | CT AMI | -2 | 660067640710010 | PM | RDD move out | PM to confirm on the dates.
6600677257 | 10010 | 4520308246 | 10 | Gleneagles Hospital Ltd | 718133 | Zenition 70 | SG90 | Ram Vinna R | Norzhar BinSalim | 2024-08-30 | 2024-06-14 | 2024-05-08 | (blank) | (blank) | (blank) | (blank) | (blank) | 2024-06-15 | Z4 Frozen <15days | No | IGT-S | -4 | 660067725710010 | FOM | Material Hold in factory | Product under RA Labelling hold, till date no firm CDD.
6600676985 | 10010 | 4520311853 | 10 | ROYAL ARC MED SOLUTION CORP. | 722228 | Azurion 5 M20 | PH90 | Charan GS | SANTIAGO GLENN | 2024-08-20 | 2024-09-06 | 2024-05-22 | (blank) | (blank) | (blank) | 2025-02-24 | (blank) | 2024-08-20 | Z4 Frozen <30days | No | IGT-S | 7 | 660067698510010 | - | > 15 days | > 15 days
6600676985 | 10090 | 4520311853 | 90 | ROYAL ARC MED SOLUTION CORP. | 722467 | Philips Hemo system with IntelliVue X3 | PH90 | Charan GS | SANTIAGO GLENN | 2024-08-20 | 2024-09-06 | 2024-05-22 | (blank) | (blank) | (blank) | 2025-02-24 | (blank) | 2024-08-20 | Z4 Frozen <30days | No | IGT-S | 7 | 660067698510090 | - | > 15 days | > 15 days
6600678065 | 20010 | 4520320088 | 10 | National University Hospital | 888121 | Ambient Experience | SG90 | Ram Vinna R | Mr Hanko Bintoro | 2024-07-01 | 2024-07-01 | 2024-05-24 | (blank) | (blank) | 2024-07-12 | (blank) | 2024-07-04 | 2024-06-01 | Z4 Frozen <30days | No | MR OEM | 9 | 660067806520010 | - | > 15 days | > 15 days
6600679508 | 30010 | 4520332131 | 10 | SIKARIN CO., LTD. | 728327 | Upgrades Ingenuity CT | TH90 | Charan GS | Janthong Wischa | 2024-10-25 | 2024-06-17 | 2024-04-29 | (blank) | 2024-04-11 | 2024-10-25 | 2024-11-29 | 2024-10-25 | 2024-10-25 | Z4 Frozen <15days | No | CT AMI | -11 | 660067950830010 | PM | Pending PM confirmation | Email follow up sent to PM
6600679090 | 10010 | 4520382600 | 10 | Thien Hanh General Hospital | 722224 | Azurion 7 M20 | VN90 | Arun Kumar | NGUYEN HUU TAI | 2024-07-26 | 2024-09-06 | 2024-05-14 | (blank) | (blank) | (blank) | 2024-10-14 | 2024-08-05 | 2024-07-26 | Z4 Frozen <15days | No | IGT-S | 1 | 660067909010010 | PM | RDD move out | PM to confirm on the dates.
6600679090 | 10090 | 4520382600 | 90 | Thien Hanh General Hospital | 722467 | Philips Hemo system with IntelliVue X3 | VN90 | Arun Kumar | NGUYEN HUU TAI | 2024-07-26 | 2024-09-06 | 2024-05-14 | (blank) | (blank) | (blank) | 2024-10-14 | (blank) | 2024-07-26 | Z4 Frozen <15days | No | IGT-S | 1 | 660067909010090 | PM | RDD move out | PM to confirm on the dates.
6600679044 | 20010 | 4520331045 | 10 | HANYANG UNIV.GURI HOSP. | 881011 | Upgrades IntelliSpace Portal | KR90 | MOON HOSUAH | LIM CS | 2024-06-30 | 2024-06-28 | 2024-05-24 | (blank) | (blank) | 2024-06-30 | 2024-08-30 | 2024-06-30 | 2024-06-30 | Z4 Frozen <30days | No | Clinical Informatics | 9 | 660067904420010 | - | > 15 days | > 15 days
6600679018 | 10010 | 4520328217 | 10 | Samsung Medical Center | 782111 | Upgrades dStream to R5.7 | KR90 | MOON HOSUAH | LIM CS | 2024-05-30 | 2024-05-30 | 2024-05-01 | (blank) | (blank) | 2024-05-30 | 2024-06-30 | 2024-05-30 | 2024-05-30 | Z4 Frozen <15days | No | MR OEM | -9 | 660067901810010 | PM | Pending PM confirmation | Pending Z4OK approval from PM
6600678936 | 10010 | 4520383262 | 10 | An Sinh Hospital | 728144 | Incisive CT | VN90 | Arun Kumar | Le Ba Tan | 2024-07-18 | 2024-08-09 | 2024-05-13 | (blank) | (blank) | (blank) | 2024-10-04 | 2024-07-18 | 2024-07-18 | Z4 Frozen <15days | No | CT AMI | 0 | 660067893610010 | PM | RDD move out | PM to confirm on the dates.
6600678888 | 10010 | 4520330249 | 10 | Loei Hospital | 722227 | Azurion 5 M12 | TH90 | Charan GS | Photichanprasert Wimolphan | 2024-10-03 | 2024-08-19 | 2024-04-16 | (blank) | 2024-04-04 | 2024-10-03 | 2024-11-08 | 2024-10-03 | 2024-10-03 | Z4 Frozen - Past | No | IGT-S | -20 | 660067888810010 | PM | Pending PM confirmation | Pending with PM
6600678888 | 10090 | 4520330249 | 90 | Loei Hospital | 722467 | Philips Hemo system with IntelliVue X3 | TH90 | Charan GS | Photichanprasert Wimolphan | 2024-10-03 | 2024-08-19 | 2024-04-16 | (blank) | 2024-04-11 | 2024-10-03 | 2024-11-08 | (blank) | 2024-10-03 | Z4 Frozen - Past | No | IGT-S | -20 | 660067888810090 | PM | Pending PM confirmation | Pending with PM
6600678199 | 10100 | 4520327446 | 10 | TRG Imaging Ltd | 712034 | DigitalDiagnost C90 High Performance | NZ90 | V Thirumalesh | Kate Wackrow | 2024-07-08 | 2024-07-08 | 2024-05-07 | (blank) | 2024-04-22 | (blank) | 2024-08-07 | (blank) | 2024-07-08 | Z4 Frozen <15days | No | DXR | -5 | 660067819910100 | PM | Pending PM confirmation | Email follow up sent to PM
6600677975 | 10100 | 4520327150 | 10 | NORTH SHORE HOSPITAL | 782142 | Upgrades dStream to R11 | NZ90 | V Thirumalesh | Kate Wackrow | 2024-05-12 | 2024-05-20 | 2024-04-26 | (blank) | 2024-04-04 | 2024-05-06 | 2024-05-13 | 2024-05-06 | 2024-05-12 | Z4 Frozen <15days | No | MR OEM | -12 | 660067797510100 | PM | Pending PM confirmation | Email follow up sent to PM
6600677975 | 10200 | 4520327150 | 20 | NORTH SHORE HOSPITAL | 781126 | SmartSpeed AI | NZ90 | V Thirumalesh | Kate Wackrow | 2024-05-12 | 2024-05-20 | 2024-04-26 | (blank) | (blank) | 2024-05-06 | 2024-05-13 | (blank) | 2024-05-12 | Z4 Frozen <15days | No | MR OEM | -12 | 660067797510200 | PM | Pending PM confirmation | Email follow up sent to PM
6600677975 | 10300 | 4520327150 | 30 | NORTH SHORE HOSPITAL | 781334 | ICAP AV | NZ90 | V Thirumalesh | Kate Wackrow | 2024-05-12 | 2024-05-20 | 2024-04-26 | (blank) | (blank) | 2024-05-06 | 2024-05-13 | (blank) | 2024-05-12 | Z4 Frozen <15days | No | Clinical Informatics | -12 | 660067797510300 | PM | Pending PM confirmation | Email follow up sent to PM
6600680321 | 10100 | 4520356889 | 10 | TOKOROA HOSPITAL | 712034 | DigitalDiagnost C90 High Performance | NZ90 | V Thirumalesh | Kate Wackrow | 2024-07-25 | 2024-07-25 | 2024-05-21 | (blank) | (blank) | 2024-07-25 | 2024-08-09 | 2024-07-25 | 2024-07-25 | Z4 Frozen <30days | No | DXR | 6 | 660068032110100 | - | > 15 days | > 15 days
6600681302 | 10010 | 4520378519 | 10 | ALFRED HEALTH | 722467 | Philips Hemo system with IntelliVue X3 | AU90 | V Thirumalesh | Consumables PCCI EShop Order | 2024-05-28 | 2024-06-13 | 2024-04-25 | (blank) | 2024-04-18 | 2024-06-03 | 2024-06-28 | 2024-05-28 | 2024-05-28 | Z4 Frozen <15days | No | IGT-S | -13 | 660068130210010 | PM | Pending PM confirmation | Email follow up sent to PM
6600681302 | 20010 | 4520378520 | 10 | ALFRED HEALTH | 722467 | Philips Hemo system with IntelliVue X3 | AU90 | V Thirumalesh | Consumables PCCI EShop Order | 2024-05-28 | 2024-06-13 | 2024-04-25 | (blank) | 2024-04-18 | 2024-06-03 | 2024-06-28 | 2024-05-28 | 2024-05-28 | Z4 Frozen <15days | No | IGT-S | -13 | 660068130220010 | PM | Pending PM confirmation | Email follow up sent to PM
6600681302 | 30010 | 4520378521 | 10 | ALFRED HEALTH | 722467 | Philips Hemo system with IntelliVue X3 | AU90 | V Thirumalesh | Consumables PCCI EShop Order | 2024-05-28 | 2024-06-13 | 2024-04-25 | (blank) | 2024-04-18 | 2024-06-03 | 2024-06-28 | 2024-05-28 | 2024-05-28 | Z4 Frozen <15days | No | IGT-S | -13 | 660068130230010 | PM | Pending PM confirmation | Email follow up sent to PM
6600680937 | 10010 | 4520373907 | 10 | Mount Elizabeth Hospital | 728272 | Upgrd Brilliance CT Big Bore | SG90 | Ram Vinna R | No Project Manager | 2024-07-30 | 2024-06-10 | 2024-04-24 | (blank) | 2024-04-23 | (blank) | (blank) | (blank) | 2024-06-10 | Z4 Frozen <15days | No | CT AMI | -14 | 660068093710010 | #N/A | #N/A | #N/A
6600680937 | 10020 | 4520373908 | 10 | Mount Elizabeth Hospital | 870227 | P16.2.1 Tumor LOC | SG90 | Ram Vinna R | No Project Manager | 2024-07-30 | 2024-07-11 | 2024-04-26 | (blank) | 2024-04-18 | (blank) | (blank) | (blank) | 2024-05-27 | Z4 Frozen <15days | No | CT AMI | -12 | 660068093710020 | #N/A | #N/A | #N/A
6600680937 | 10030 | 4520373908 | 20 | Mount Elizabeth Hospital | 870240 | TumorLOC Server | SG90 | Ram Vinna R | No Project Manager | 2024-07-30 | 2024-07-11 | 2024-04-26 | (blank) | 2024-04-18 | (blank) | (blank) | (blank) | 2024-05-27 | Z4 Frozen <15days | No | CT AMI | -12 | 660068093710030 | #N/A | #N/A | #N/A
0077498438 | 10010 | 4520383573 | 10 | SJP Medical Centres Sdn. Bhd. | 722223 | Azurion 7 M12 | MY91 | Swamynathan s | Yong Kim Loong | 2024-04-17 | 2024-08-30 | 2024-05-03 | (blank) | 2024-04-22 | (blank) | (blank) | (blank) | 2024-08-31 | Z4 Frozen <15days | No | IGT-S | -7 | 007749843810010 | PM | Pending PM confirmation | Email follow up sent to PM
0077498438 | 30010 | 4520383574 | 10 | SJP Medical Centres Sdn. Bhd. | 722224 | Azurion 7 M20 | MY91 | Swamynathan s | Yong Kim Loong | 2024-04-17 | 2024-08-30 | 2024-05-02 | (blank) | 2024-04-23 | (blank) | (blank) | (blank) | 2024-08-31 | Z4 Frozen <15days | No | IGT-S | -8 | 007749843830010 | PM | Pending PM confirmation | Email follow up sent to PM
0077498438 | 30130 | 4520383574 | 130 | SJP Medical Centres Sdn. Bhd. | 722467 | Philips Hemo system with IntelliVue X3 | MY91 | Swamynathan s | Yong Kim Loong | 2024-04-17 | 2024-08-30 | 2024-05-09 | (blank) | (blank) | (blank) | (blank) | (blank) | 2024-08-31 | Z4 Frozen <15days | No | IGT-S | -3 | 007749843830130 | PM | Pending PM confirmation | Email follow up sent to PM
0077498438 | 30340 | 4520383574 | 140 | SJP Medical Centres Sdn. Bhd. | 722370 | Interfacing with Partners | MY91 | Swamynathan s | Yong Kim Loong | 2024-04-17 | 2024-09-06 | 2024-05-16 | (blank) | (blank) | (blank) | (blank) | (blank) | 2024-08-31 | Z4 Frozen <30days | No | IGT-S | 3 | 007749843830340 | - | > 15 days | > 15 days
0077495838 | 10010 | 4520129426 | 10 | HOSPITAL MIRI | 782112 | SmartPath to dStream for 1.5T | MY91 | Swamynathan s | Arvin Kanan | 2024-07-15 | 2024-07-31 | 2024-05-01 | (blank) | 2024-04-14 | (blank) | (blank) | (blank) | 2024-07-15 | Z4 Frozen <15days | No | MR OEM | -9 | 007749583810010 | PM | Pending PM confirmation | PM asked to hold the CDD, factory accepted to hold CDD till April end
0077495838 | 10020 | 4520129426 | 20 | HOSPITAL MIRI | 782300 | RF Coils 1.5T and Biopsy kits | MY91 | Swamynathan s | Arvin Kanan | 2024-07-15 | 2024-07-31 | 2024-05-01 | (blank) | 2024-04-14 | (blank) | (blank) | (blank) | 2024-07-15 | Z4 Frozen <15days | No | MR OEM | -9 | 007749583810020 | PM | Pending PM confirmation | PM asked to hold the CDD, factory accepted to hold CDD till April end
0077482341 | 10010 | 4518451574 | 10 | KPJ Sabah Specialist Hospital | 722223 | Azurion 7 M12 | MY91 | Swamynathan s | Arvin Kanan | 2023-09-01 | 2024-08-19 | 2024-04-21 | (blank) | 2023-08-15 | 2024-09-30 | 2024-10-21 | 2024-09-16 | 2024-09-16 | Z4 Frozen - Past | No | IGT-S | -16 | 007748234110010 | FOM | RDD move out | RDD revised to Sep 16
0077460738 | 10010 | 4516165105 | 10 | HOSPITAL SIBU | 889227 | Achieva dStream 1.5T - DS | MY91 | Swamynathan s | Arvin Kanan | 2023-07-15 | 2024-07-15 | 2024-04-15 | (blank) | 2021-02-16 | 2024-07-24 | 2024-08-14 | 2024-07-15 | 2024-07-15 | Z4 Frozen - Past | No | MR OEM | -21 | 007746073810010 | PM | Pending PM confirmation | Email follow up sent to PM
0077460738 | 10040 | 4516165105 | 20 | HOSPITAL SIBU | 889218 | Magnet | MY91 | Swamynathan s | Arvin Kanan | 2023-07-15 | 2024-07-15 | 2024-05-16 | (blank) | (blank) | 2024-07-24 | 2024-08-14 | (blank) | 2024-07-15 | Z4 Frozen <30days | No | MR OEM | 3 | 007746073810040 | - | > 15 days | > 15 days
0006006096 | 10030 | 4516069369 | 10 | Advanced Medicine Imaging Pte Ltd | 881101 | Convert IntelliSpace Portal to future | SG90 | Ram Vinna R | B. Lyn | 2021-03-31 | 2022-12-31 | 2023-12-01 | (blank) | (blank) | (blank) | 2021-09-30 | (blank) | 2021-02-08 | Z4 Frozen - Past | No | Clinical Informatics | -117 | 000600609610030 | PM | Pending PM confirmation | PM to confim on the cancellation
6600683112 | 10010 | 4520397385 | 10 | National Heart Centre of Singapore | 722141 | Technology Maximizer Allura | SG90 | Ram Vinna R | Ram Vinna R | 2024-05-21 | 2024-06-13 | 2024-04-23 | (blank) | 2024-04-23 | (blank) | (blank) | (blank) | 2024-05-21 | Z4 Frozen - Past | No | PD Other | -15 | 660068311210010 | #N/A | #N/A | #N/A
Formulas:
Days until Start FP = IF([Start Frozen Period Date]>=TODAY(),(NETWORKDAYS(TODAY(),[Start Frozen Period Date])-1),(NETWORKDAYS(TODAY(),[Start Frozen Period Date])))

## Mapping (hidden)
Ref | Owner | Comments - High | Detialed Comments
000600609610030 | PM | Pending PM confirmation | PM to confim on the cancellation
660064243910010 | PM | Pending PM confirmation | Order to be debooked by end of April
660064005510040 | FOM | RDD move out | RDD changed to 31.03.2025; Waiting for revised FSD7 FP
660064005510050 | FOM | RDD move out | RDD changed to 31.03.2025; Waiting for revised FSD7 FP
660058807310010 | PM | Pending PM confirmation | Pending with PM; Planning to swap
660066115810030 | FOM | RDD move out | Not relvant for Z4
660066115810040 | FOM | RDD move out | Not relvant for Z4
660058807310090 | PM | Pending PM confirmation | Pending with PM; Planning to swap
007746073810010 | PM | Pending PM confirmation | Email follow up sent to PM
660067888810010 | PM | Pending PM confirmation | Pending with PM
660067888810090 | PM | Pending PM confirmation | Pending with PM
660060170610010 | PM | Pending PM confirmation | Cancelled in PSA
660060170610030 | PM | Pending PM confirmation | Cancelled in PSA
660060170610040 | PM | Pending PM confirmation | Cancelled in PSA
660066045410010 | PM | Pending PM confirmation | Pending with PM
007748234110010 | FOM | RDD move out | RDD revised to Sep 16
660061750310010 | FOM | RDD move out | RDD move out- revised FPD required
660066903910010 | FOM | RDD move out | RDD move out- revised FPD required
660068130210010 | PM | Pending PM confirmation | Email follow up sent to PM
660068130220010 | PM | Pending PM confirmation | Email follow up sent to PM
660068130230010 | PM | Pending PM confirmation | Email follow up sent to PM
660065515410010 | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness
660065515410030 | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness
660065515410040 | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness
660067470610010 | PM | Pending PM confirmation | Email follow up sent to PM
660067470610020 | PM | Pending PM confirmation | Email follow up sent to PM
660067797510100 | PM | Pending PM confirmation | Email follow up sent to PM
660067797510200 | PM | Pending PM confirmation | Email follow up sent to PM
660067797510300 | PM | Pending PM confirmation | Email follow up sent to PM
660061750310110 | PM | Pending PM confirmation | Email follow up sent to PM
660065835820010 | PM | Pending PM confirmation | Email follow up sent to PM
660067950830010 | PM | Pending PM confirmation | Email follow up sent to PM
660063762820010 | PM | Pending PM confirmation | Email follow up sent to PM
660067901810010 | PM | Pending PM confirmation | Pending Z4OK approval from PM
007749583810010 | PM | Pending PM confirmation | PM asked to hold the CDD, factory accepted to hold CDD till April end
007749583810020 | PM | Pending PM confirmation | PM asked to hold the CDD, factory accepted to hold CDD till April end
007749583810030 | PM | Pending PM confirmation | PM asked to hold the CDD, factory accepted to hold CDD till April end
660067670120040 | PM | Pending PM confirmation | Issue in PSA to set Z4 fromPM
007749843830010 | PM | Pending PM confirmation | Email follow up sent to PM
660061723910010 | PM | Pending PM confirmation | Pending with PM
007749843810010 | PM | Pending PM confirmation | Email follow up sent to PM
660062939710010 | PM | Pending PM confirmation | Email follow up sent to PM
660062939710020 | PM | Pending PM confirmation | Email follow up sent to PM
660062939710030 | PM | Pending PM confirmation | Email follow up sent to PM
660063348310010 | PM | Pending PM confirmation | Pending Z4OK approval from PM
660064138740010 | PM | Pending PM confirmation | Email follow up sent to PM
660065516310020 | PM | Pending PM confirmation | Email follow up sent to PM
660065516310030 | PM | Pending PM confirmation | Email follow up sent to PM
660066423040010 | PM | Pending PM confirmation | Email follow up sent to PM
660067819910100 | PM | Pending PM confirmation | Email follow up sent to PM
660067725710010 | FOM | Material Hold in factory | Product under RA Labelling hold, till date no firm CDD.
660064198710010 | PM | Pending PM confirmation | Pending Z4OK approval from PM
660066115810010 | PM | RDD move out | PM to confirm on the dates.
007749843830130 | PM | Pending PM confirmation | Email follow up sent to PM
660067640710010 | PM | RDD move out | PM to confirm on the dates.
660063791250020 | PM | Pending PM confirmation | Email follow up sent to PM
660063791250030 | PM | Pending PM confirmation | Email follow up sent to PM
660065516310010 | PM | Pending PM confirmation | Email follow up sent to PM
660067893610010 | PM | RDD move out | PM to confirm on the dates.
660056508110010 | PM | Pending PM confirmation | Email follow up sent to PM
660061723910090 | FOM | CCD SWAP | Swap allocation request sent to FOM
660065515410020 | PM | Pending PM confirmation | Pending from PM for confirmation on Site readiness
660067909010010 | PM | RDD move out | PM to confirm on the dates.
660067909010090 | PM | RDD move out | PM to confirm on the dates.
660056508110090 | PM | Pending PM confirmation | Email follow up sent to PM
660047066120010 | PM | Pending PM confirmation | -
660063394410020 | PM | Pending PM confirmation | -
660059261050010 | PM | Pending PM confirmation | -
660058472560010 | FOM | RDD move out- revised FPD required | -
660058472570010 | FOM | RDD move out- revised FPD required | -
660058472580010 | FOM | RDD move out- revised FPD required | -
660063406210010 | FOM | RDD move out- revised FPD required | -
660063406210030 | FOM | RDD move out- revised FPD required | -
660063406210050 | FOM | RDD move out- revised FPD required | -
660063406210060 | FOM | RDD move out- revised FPD required | -
660063806110010 | PM | Pending PM confirmation | -
660062181610010 | PM | Pending PM confirmation | Waiting for PM to confirm Z4/RDD changes
660063663110010 | PM | Pending PM confirmation | -
660063663110020 | PM | Pending PM confirmation | -
660060140110010 | PM | Pending PM confirmation | -
660062875610010 | PM | Pending PM confirmation | -
660062875710010 | PM | Pending PM confirmation | -
660063617420010 | PM | Pending PM confirmation | -
660062732240010 | PM | Pending PM confirmation | -
660062732250010 | PM | Pending PM confirmation | -
660062732260010 | PM | Pending PM confirmation | -
660063769110100 | PM | Pending PM confirmation | -
660063806210010 | PM | Pending PM confirmation | -
660063990110010 | PM | Pending PM confirmation | -
660061861710090 | PM | Pending PM confirmation | -
660062030110100 | PM | Pending PM confirmation | -
660062030110110 | PM | Pending PM confirmation | -
660062686610030 | PM | Pending PM confirmation | -
660062875010010 | PM | Pending PM confirmation | -
660062875010020 | PM | Pending PM confirmation | -
660062875010030 | PM | Pending PM confirmation | -
660062971710030 | FOM | RDD move out- revised FPD required | -
660063726210020 | PM | Pending PM confirmation | -
660063806310010 | PM | Pending PM confirmation | -
660063806320010 | PM | Pending PM confirmation | -
660064139510010 | PM | Pending PM confirmation | -
660064139510090 | PM | Pending PM confirmation | -
000626386010010 | PM | Pending PM confirmation | RDD changed to 10 Nov on 16 May; IDOC issue; Waiting for revised FSD & FP
660060191210010 | PM | Pending PM confirmation | -
660061693240030 | PM | Pending PM confirmation | -
660061693250010 | PM | Pending PM confirmation | -
660063762520010 | PM | Pending PM confirmation | -
660060412010010 | PM | Pending PM confirmation | -
660062294810010 | PM | Pending PM confirmation | -
660062294820010 | PM | Pending PM confirmation | -
660062294830010 | PM | Pending PM confirmation | -
660062294870010 | PM | Pending PM confirmation | -
660063647710010 | PM | Pending PM confirmation | -
660063647710020 | PM | Pending PM confirmation | -
660063763610010 | PM | Pending PM confirmation | -
660062972710010 | PM | Pending PM confirmation | -
6600575452130010 | PM | Pending PM confirmation | -
660060669030010 | PM | Pending PM confirmation | -
660060669040010 | PM | Pending PM confirmation | -
660060669050010 | PM | Pending PM confirmation | -
660062030110010 | PM | Pending PM confirmation | -
660062244210010 | PM | Pending PM confirmation | -
660062244210100 | PM | Pending PM confirmation | -
660062244210300 | PM | Pending PM confirmation | -
660062445910240 | PM | Pending PM confirmation | -
660062828410010 | PM | Pending PM confirmation | -
660063762510010 | PM | Pending PM confirmation | -
660056647810010 | PM | Pending PM confirmation | -
660056647820010 | PM | Pending PM confirmation | -
660056647830010 | PM | Pending PM confirmation | -
660061814510010 | PM | Pending PM confirmation | Waiting for PM to confirm Z4/RDD changes
660061975520010 | PM | Pending PM confirmation | -
660061975520020 | PM | Pending PM confirmation | -
660061975710030 | PM | Pending PM confirmation | -
660061975710040 | PM | Pending PM confirmation | -
660062083320010 | PM | Pending PM confirmation | -
660062361810030 | PM | Pending PM confirmation | -
660062361810040 | PM | Pending PM confirmation | -
660062937620020 | PM | Pending PM confirmation | -
660063045810010 | PM | Pending PM confirmation | -
660063411710010 | PM | Pending PM confirmation | -
660063411720010 | PM | Pending PM confirmation | -
660063411720020 | PM | Pending PM confirmation | -
660063609010010 | PM | Pending PM confirmation | -
660063609010020 | PM | Pending PM confirmation | -
660063609010030 | PM | Pending PM confirmation | -
660063994910010 | PM | Pending PM confirmation | -
660062275210010 | PM | Pending PM confirmation | -
660062275220010 | PM | Pending PM confirmation | -
660062275220090 | PM | Pending PM confirmation | -
660063003620010 | PM | Pending PM confirmation | -
660063482910010 | PM | Pending PM confirmation | -
660063722110010 | PM | Pending PM confirmation | -
660057507610010 | PM | Pending PM confirmation | -
660057507610080 | PM | Pending PM confirmation | -
660057507610090 | PM | Pending PM confirmation | -
660059431510010 | PM | Pending PM confirmation | -
660062083310010 | PM | Pending PM confirmation | -
660062083310020 | PM | Pending PM confirmation | -
660062083310200 | PM | Pending PM confirmation | -
660062361810010 | PM | Pending PM confirmation | Waiting for market confirmation for Z4
660062690610010 | PM | Pending PM confirmation | -
660062985510010 | PM | Pending PM confirmation | -
660062985530010 | PM | Pending PM confirmation | -
660063029110010 | PM | Pending PM confirmation | -
660063029110030 | PM | Pending PM confirmation | -
660063029110040 | PM | Pending PM confirmation | -
660063029110050 | PM | Pending PM confirmation | -
660063046110010 | PM | Pending PM confirmation | -
660063003610010 | PM | Pending PM confirmation | -
660063746710010 | PM | Pending PM confirmation | -
660058472590010 | PM | Pending PM confirmation | -
660063398310010 | PM | Pending PM confirmation | -
660058472540030 | PM | Pending PM confirmation | -
660062181610030 | PM | Pending PM confirmation | -
660062181610040 | PM | Pending PM confirmation | -
660062919010100 | PM | Pending PM confirmation | -
660062972720010 | PM | Pending PM confirmation | -
660060252710010 | PM | Pending PM confirmation | -
660060252710050 | PM | Pending PM confirmation | -
660063288810010 | PM | Pending PM confirmation | -
660063288810030 | PM | Pending PM confirmation | -
660063288810050 | PM | Pending PM confirmation | -
660063288810060 | PM | Pending PM confirmation | -
660059530220010 | PM | Pending PM confirmation | -
660059530220020 | PM | Pending PM confirmation | -
660061225310010 | PM | Pending PM confirmation | -
660062690620010 | PM | Pending PM confirmation | -
660062690620020 | PM | Pending PM confirmation | -
660063045820010 | PM | Pending PM confirmation | -
660063045820020 | PM | Pending PM confirmation | -
660063046120010 | PM | Pending PM confirmation | -
660063046120020 | PM | Pending PM confirmation | -
660063482910090 | PM | Pending PM confirmation | -
660063483210010 | PM | Pending PM confirmation | -
660062875610090 | PM | Pending PM confirmation | -
660062875710090 | PM | Pending PM confirmation | -
007748234110090 | FOM | RDD move out | RDD revised to Sep 16
660058996910010 | FOM | RDD move out | RDD has been changed on march 22nd itself and sent mail to FOM and planning team.
660058996910090 | FOM | RDD move out | RDD has been changed on march 22nd itself and sent mail to FOM and planning team.
660060675710010 | PM | Pending PM confirmation | market is checking on configuration before confirming to set Z4
660060832610010 | Cancel | For Cancellation | Slot swapped and will be cancelled
660061723920010 | PM | Pending PM confirmation | FPO cancelled
007749403910010 | PM | Pending PM confirmation | Pending for config change
660065425910010 | FOM | RDD move out | RDD move out- revised FPD required
660065695810010 | FOM | Pending Factory Confirmation | PM sent OVL document to FOM for confirmation once confirmed we will set Z4
660065957710010 | PM | Pending PM confirmation | Pending with PM
660066246510010 | PM | Pending PM confirmation | Pending with PM
660066597210010 | PM | Pending PM confirmation | PM working on it. Expecting to receive this week or Z4 confirmation or RDD moveout
660067187010010 | PM | Pending PM confirmation | Already Following up with PM for Z4 , they are working on it and FP date is on 16th april
660067281510010 | PM | Pending PM confirmation | PM working on it. Expecting to receive this week or Z4 confirmation or RDD moveout
660067806510010 | FOM | Pending Factory Confirmation | PM sent OVL document to FOM for confirmation once confirmed we will set Z4
660067806510100 | FOM | Pending Factory Confirmation | PM sent OVL document to FOM for confirmation once confirmed we will set Z4
660067806510110 | FOM | Pending Factory Confirmation | PM sent OVL document to FOM for confirmation once confirmed we will set Z4
660067910510010 | PM | Pending PM confirmation | Pending with PM
660067910510090 | PM | Pending PM confirmation | Pending with PM
660067901110010 | Closed | Z4 submitted | Z4 submitted
660067838510010 | PM | Pending PM confirmation | FP date is on 1st may only
660062732310010 | PM | Pending PM confirmation | Email follow up sent to PM
660065803910010 | PM | Pending PM confirmation | Config issues need update, Email follow up sent to PM
6600662625110010 | PM | Pending PM confirmation | First email notif sent to PM
6600662625110030 | PM | Pending PM confirmation | First email notif sent to PM
6600662625110040 | PM | Pending PM confirmation | First email notif sent to PM
6600662625120010 | PM | Pending PM confirmation | First email notif sent to PM
6600662625120030 | PM | Pending PM confirmation | First email notif sent to PM
6600662625120040 | PM | Pending PM confirmation | First email notif sent to PM
660067353910100 | PM | Pending PM confirmation | Email follow up sent to PM
660067326510100 | PM | Pending PM confirmation | First email notif sent to PM
660067376610010 | PM | Pending PM confirmation | Email follow up sent to PM
660067456710100 | PM | Pending PM confirmation | First email notif sent to PM
660067456710200 | PM | Pending PM confirmation | First email notif sent to PM
660067456710300 | PM | Pending PM confirmation | First email notif sent to PM
660067812710010 | PM | Pending PM confirmation | Email follow up sent to PM
660067910110100 | FOM | RDD move out | RDD has been move out , pending new SFP
660062836810010 | PM | Pending PM confirmation | Pending with PM
660064653740010 | PM | Pending PM confirmation | Pending with PM
660064653750010 | PM | Pending PM confirmation | Pending with PM
660064653760010 | PM | Pending PM confirmation | Pending with PM
660067433010020 | - | No Z4 required | No Z4 required
660067438920010 | - | No Z4 required | No Z4 required
660067682010010 | PM | Pending PM confirmation | Pending with PM
660067910330010 | PM | Pending PM confirmation | Pending with PM
660056647950010 | - | > 15 days | > 15 days
660062542110010 | - | > 15 days | > 15 days
660062542110030 | - | > 15 days | > 15 days
660063348330010 | - | > 15 days | > 15 days
660063791250010 | - | > 15 days | > 15 days
660064298410010 | - | > 15 days | > 15 days
660064298420010 | - | > 15 days | > 15 days
660065835820030 | - | > 15 days | > 15 days
660066045410100 | - | > 15 days | > 15 days
660066262510010 | - | > 15 days | > 15 days
660066262580010 | - | > 15 days | > 15 days
660066302720010 | - | > 15 days | > 15 days
660066302720020 | - | > 15 days | > 15 days
660066423110010 | - | > 15 days | > 15 days
660067370320010 | - | > 15 days | > 15 days
660067326520100 | - | > 15 days | > 15 days
660067438510010 | - | > 15 days | > 15 days
660067698510010 | - | > 15 days | > 15 days
660067698510090 | - | > 15 days | > 15 days
660067806520010 | - | > 15 days | > 15 days
660067904420010 | - | > 15 days | > 15 days
660068032110100 | - | > 15 days | > 15 days
007749843830340 | - | > 15 days | > 15 days
007746073810040 | - | > 15 days | > 15 days